## Sheet1
Phase | Step | Task | Output | Tech | Status | Priority
Core | 1 | DNA Axes v1 | 10 axe canonice definite | JSON model | ✅ DONE | High
Core | 2 | Core Journey model | flow utilizator complet | state machine logic | ✅ DONE | High
Core | 3 | Recommendation engines | discovery + compatibility | engine spec | ✅ DONE | High
Core | 4 | Fragrance canonical DB | structură parfumuri + metadata | JSON dataset | ✅ DONE | High
Core | 5 | User attribute layer v3 | semantic mapping user ↔ parfum | mapping system | ✅ DONE | High
Engine | 1 | Compatibility Engine spec | scoring logic definit | algorithm spec | ✅ DONE | High
Engine | 2 | Discovery Engine spec | gap-based learning model | algorithm spec | ✅ DONE | High
Engine | 3 | DNA refinement loop | feedback → update profile | iterative model | 🟡 PARTIAL (concept) | High
Engine | 4 | Coverage model | completare profil utilizator | theoretical layer | 🟡 PARTIAL | High
MVP Web | 1 | Setup proiect Next.js | proiect rulabil local | Next.js | Not started | High
MVP Web | 2 | Structură UI base | layout simplu (home + flow) | React | Not started | High
MVP Web | 3 | Test Flow UI v1 | 1 parfum / ecran | React state | Not started | High
MVP Web | 4 | Load FragranceDB JSON | data conectată | JSON import | 🟡 PARTIAL (exists) | High
MVP Web | 5 | Slider evaluation UI | 7-step scale | UI component | Not started | High
MVP Web | 6 | Basic scoring engine | calc profil user | JS logic | Not started | High
MVP Web | 7 | Next fragrance selection | logic de progresie | algorithm | Not started | High
MVP Web | 8 | Results page v1 | top 5 recomandări | ranking algo | Not started | High
Engine | 1 | Upgrade scoring v4 | matching avansat | JS/TS | Not started | High
Engine | 2 | Axis weighting system | personalizare | algorithm | Not started | High
Engine | 3 | Similarity engine | parfumuri apropiate | vector math | Not started | High
Engine | 4 | User profile persistence | salvare profil | localStorage | Not started | Medium
Backend | 1 | API layer | endpoints engine | Node.js | Not started | Medium
Backend | 2 | Save user sessions | profile storage | DB | Not started | Medium
Backend | 3 | Authentication | user accounts | Auth | Not started | Low
Mobile | 1 | React Native app | mobile version | React Native | Not started | Low
Mobile | 2 | Shared engine | reuse logic | TS shared lib | Not started | Low